## SHIP WD
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (SE-RDA) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887

## Codes
This sheet has all the options for the dropdown lists on the main sheet. Blank rows have been left to allow extra options to be added in the future - please do not delete them.
SLP Status
17/18
18/19
19/20 | Priority
20/21 | L
21/22 | M
22/23 | H
23/24
Developer | AHP Contibution site
FC | Y
FC PSD | N
KHA
KI
FHG
OVHA
Ark HA
Link HA
Landlord
FC
FC PSD
KHA
KI
FHG (A)
OVHA
GHA
FHG
Ark HA
Link HA
LHS Area |  | HMA Area
Glenrothes |  | Dunfermline & West Fife
Kirkcaldy |  | Kirkcaldy, Glenrothes & Central
Levenmouth |  | Cupar & North West Fife
Dunfermline & Coast |  | St Andrews & East Fife
Cowdenbeath |  | Greater Dundee
West Fife Villages
Cupar & HOF
Largo & East Neuk
St Andrews
Tay Coast
Years
2017/18
2018/19
2019/20
2020/21
2021/22
2022/23
2023/24
2024/25
2025/26
2026/27
2027/28
2028/29
2029/30
2030/31
2031/32
2032/33
2033/34
Tenure
SR
MMR 30
MMR 5
PSR
Other
Contract Type
D&B
OTS
FC BS
Staged
SCAPE
Change Control
Add - to be approved
Removed - to be approved
Other Change - lead delivery partner
Other Change - see comments
Stage
0 - Feasibility
1 - Dev Mix & brief
2 - design, plg & acq
3 - Contract Neg/tender approval
4 - on site
5 - completed
Block
A
B
Shadow
Programmed/Potential
Programmed
Potential
Phase 5 tbc
Shadow
Below List
Phase 4 Yr 1 & 2
Phase 4 Yr 3 to 5

## Abbreviations
Project Name
EC Housing | Extra Care Housing
MMR | Mid-Market Rent
MS | Microsite
OPH | Older Person's Housing
PSD | Private Sector Development
SE-RDA | South East Regional Delivery Alliance
SDA | Strategic Development Area
SR | Social Rent
Developer/Landlord
FC | Fife Council
FHG | Fife Housing Group
GHA | Glen Housing Association
KI | Kingdom Initiatives
OVHA | Ore Valley Housing Association
Contract Type
D&B | Design & Build
FC BS | Fife Council Building Services
OTS | Off the Shelf

## Cowdenbeath
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 338 | 245 | 122 | 44 |  | 1053 | 490 | 162 |  | 28 | 110 | 79 | 28 | 0 | 0 |  | 26 | 69 | 13 | 8 | 4 | 2

## Cupar & HOF
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 125 | 180 | 62 | 8 |  | 764 | 285 | 30 |  | 4 | 107 | 59 | 10 | 0 | 0 |  | 0 | 45 | 3 | 14 | 0 | 0

## Dunf & Coast
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 828 | 669 | 250 | 71 |  | 2974 | 1014 | 268 |  | 32 | 359 | 219 | 57 | 2 | 0 |  | 59 | 139 | 14 | 10 | 28 | 0

## Glenrothes
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 280 | 212 | 100 | 18 |  | 1108 | 352 | 63 |  | 0 | 132 | 58 | 22 | 0 | 0 |  | 17 | 58 | 10 | 0 | 15 | 0

## Kirkcaldy
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 326 | 332 | 126 | 29 |  | 1419 | 484 | 124 |  | 27 | 186 | 70 | 49 | 0 | 0 |  | 19 | 91 | 1 | 0 | 15 | 0

## Largo & East Neuk
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 66 | 49 | 31 | 3 |  | 175 | 106 | 4 |  | 0 | 26 | 19 | 4 | 0 | 0 |  | 15 | 15 | 0 | 1 | 0 | 0

## Levenmouth
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (SE-RDA) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 139 | 95 | 36 | 8 |  | 444 | 161 | 29 |  | 0 | 49 | 35 | 11 | 0 | 0 |  | 0 | 23 | 9 | 1 | 3 | 0

## St Andrews
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 106 | 118 | 51 | 7 |  | 523 | 214 | 61 |  | 0 | 79 | 33 | 6 | 0 | 0 |  | 0 | 42 | 5 | 3 | 1 | 0

## Tay Coast
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 58 | 28 | 25 | 5 |  | 130 | 104 | 20 |  | 0 | 12 | 14 | 2 | 0 | 0 |  | 0 | 24 | 0 | 0 | 1 | 0

## West Fife Villages
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2026/27 - 2030/31)
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2026/27 | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant 2030/2031 (£m) | SG Grant Post 2030/2031 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | Priority (LMH) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Comment
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April | 0 |  | 0.902 |  |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | May | 35 | 21 | 12 | 2 | 150 | 88 | 54 | 8 | 21 | 0 | 17 | 4 | 0 | 0 | 0 | 12 | 0 | 10 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 5.714% | SR | D&B | 2028/29 | May | 2030/31 | April | 0 |  |  | 2.151 | 1.5 |  |  | 3.651 |  |  |  |  | 3.651 | 0.10431 | M | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110
P47652 | Main Street, Inchcolm Green | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | December | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | February | 2026/27 | August | 1.1719 | [6 empty] | 1.1719 |  |  | 1 |  | 2.1719 | 0.10342 | H | 40 | 20 | 90 | 70 | 0 | 10 | 60 | 160 | 10 | 230
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 20 | 14 | 4 | 2 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | September | 0 |  |  |  | 0.7 | 0.88706 |  | 1.5871 | Y |  | 0.5 |  | 2.0871 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2026/27 | September | 15 | 0 | 15 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2026/27 | September | 2028/29 | May | 0 | 0.5 | 0.7153 |  |  |  |  | 1.2153 | Y |  | 0.35 |  | 1.5653 | 0.10435 | H | 30 | 35 | 50 | 30 | 20 | 30 | 65 | 80 | 50 | 195
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2029/30 | March | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | March | 2031/32 | November | 0 |  |  |  | 1.769 | 1.561 |  | 3.33 |  |  |  |  | 3.33 | 0.111 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90 | 30 units to be delivered | 30
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2030/31 | August | 0 | 16 | 18 | 6 | 195 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 60% | 15% | SR | D&B | 2030/31 | August | 2032/33 | March | 0 |  |  |  |  | 1.418 | 2 | 3.418 |  |  |  |  | 3.418 | 0.08545 | L | 40 | 10 | 0 | 10 | 0 | 10 | 50 | 10 | 10 | 70 | 40 units to be delivered | 40
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2030/31 | January | 0 | 11 | 3 | 1 | 154 | 80 | 70 | 4 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2030/31 | January | 2032/33 | October | 0 |  |  |  |  | 1.565 |  | 1.565 | Y |  |  |  | 1.565 | 0.10433 | M | 40 | 40 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | March | 18 | 13 | 4 | 1 | 84 | 62 | 18 | 4 | 13 | 0 | 7 | 4 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | March | 2026/27 | June | 1.4808 | [6 empty] | 1.4808 | Y |  | 0.4 | 0.048167 | 1.929 | 0.10717 | H | 40 | 40 | 90 | 30 | 0 | 20 | 80 | 120 | 20 | 220
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 63 | 45 | 11 | 7 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2026/27 | January | 2028/29 | November | 0 | 0.6 | 3.196 | 3.196 |  |  |  | 6.992 | Y |  |  |  | 6.992 | 0.11098 | H | 40 | 40 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  |  | 3.252 | 0.1084 | H | 40 | 40 | 50 | 30 | 0 | 10 | 80 | 80 | 10 | 170 | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | 0 |  |  | 0.555 | 0.555 |  |  | 1.11 |  |  |  |  | 1.11 | 0.111 | M | 50 | 25 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125
P48428 | South of Main Street | Coaltown Wemyss | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | January | 3 | 3 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | January | 2027/28 | October | 0 |  | 0.31293 |  |  |  |  | 0.31293 |  |  |  |  | 0.31293 | 0.10431 | H | 50 | 50 | 40 | 70 | 0 | 10 | 100 | 110 | 10 | 220
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | July | 15 | 11 | 4 | 0 | 71 | 39 | 32 | 0 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.67% | 0% | SR | D&B | 2025/26 | July | 2026/27 | October | 2.03 | [6 empty] | 2.03 |  |  |  |  | 2.03 | 0.13533 | H | 30 | 35 | 30 | 70 | 0 | 10 | 65 | 100 | 10 | 175
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | March | 0 | 29 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | 0 |  |  |  | 0.1 | 3.119 |  | 3.219 | Y |  |  |  | 3.219 | 0.111 | M | 40 | 10 | 0 | 30 | 20 | 10 | 50 | 30 | 30 | 110 | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | November | 12 | 7 | 0 | 5 | 51 | 28 | 0 | 23 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 41.67% | 41.67% | SR | D&B | 2029/30 | November | 2030/31 | October | 0 |  |  |  | 1.1474 |  |  | 1.1474 |  |  |  |  | 1.1474 | 0.095618 | M | 40 | 10 | 0 | 30 | 20 | 30 | 50 | 30 | 50 | 130
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | October | 54 | 43 | 10 | 1 | 216 | 140 | 72 | 4 | 43 | 3 | 15 | 21 | 4 | 0 | 0 | 10 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 20.37% | 1.852% | SR | D&B | 2025/26 | October | 2028/29 | January | 0 | 4.534 | 2 |  |  |  |  | 6.534 | Y |  |  |  | 6.534 | 0.121 | H | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180
P48547 | Coaledge | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 28 | 17 | 9 | 2 | 128 | 77 | 43 | 8 | 17 | 0 | 8 | 9 | 0 | 0 | 0 | 9 | 0 | 4 | 4 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 39.29% | 7.143% | SR | D&B | 2027/28 | January | 2029/30 | April | 0 |  | 0.8 | 2.308 |  |  |  | 3.108 |  |  |  |  | 3.108 | 0.111 | L | 40 | 10 | 10 | 10 | 0 | 10 | 50 | 20 | 10 | 80
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | ¦January | 10 | 6 | 3 | 1 | 38 | 22 | 12 | 4 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 40% | 10% | SR | D&B | 2026/27 | January | 2027/28 | March | 0 |  | 0.84312 |  |  |  |  | 0.84312 | Y |  | 0.2 |  | 1.0431 | 0.10431 | L | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2030/31 | April | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 0.41724 |  | 0.41724 | Y |  |  |  | 0.41724 | 0.10431 | M | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 4 units to be delivered | 4
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 17 | 8 | 0 | 106 | 72 | 34 | 0 | 0 | 0 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | April | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | April | 2031/32 | March | 0 |  |  |  | 0.486 |  |  | 0.486 |  |  |  |  | 0.486 | 0.081 | M | 20 | 30 | 10 | 30 | 20 | 10 | 50 | 40 | 30 | 120 | 6 units to be delivered | 6
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | 0 |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 12 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.972 |  |  | 0.972 |  |  |  |  | 0.972 | 0.081 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 25 | 13 | 0 | 165 | 106 | 59 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | 0 |  |  |  | 0.6 | 3.123 |  | 3.723 |  |  |  |  | 3.723 | 0.097974 | M | 20 | 30 | 10 | 30 | 0 | 10 | 50 | 40 | 10 | 100 | 38 units to be delivered | 38
P44735 | Inner Court (KHA) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | November | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 1 | 0.608 | [5 empty] | 1.608 | Y |  |  | 0.0132 | 1.6212 | 0.12471 | H | 20 | 30 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | November | 10 | 10 | 0 | 0 | 34 | 34 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | November | 2027/28 | October | 0 |  | 1.081 |  |  |  |  | 1.081 | Y |  | 0.6 |  | 1.681 | 0.1681 | H | 20 | 30 | 30 | 70 | 20 | 10 | 50 | 100 | 30 | 180
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2027/28 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | January | 2028/29 | June | 0 |  | 1.7371 |  |  |  |  | 1.7371 | Y |  | 0.35 |  | 2.0871 | 0.10435 | H | 20 | 30 | 50 | 30 | 20 | 20 | 50 | 80 | 40 | 170
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2025/26 | October | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2025/26 | October | 2027/28 | April | 3.0982 | 3.644 | [5 empty] | 6.7422 | Y |  |  |  | 6.7422 | 0.1376 | H | 20 | 30 | 50 | 70 | 0 | 20 | 50 | 120 | 20 | 190
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | June | 20 | 14 | 6 | 0 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2028/29 | June | 2030/31 | March | 0 |  |  | 1 | 0.959 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | L | 20 | 30 | 0 | 30 | 0 | 10 | 50 | 30 | 10 | 90
P46874 | Aberdour Road / Evershed Drive (Older Persons Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | June | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | July | 2027/28 | Sept | 2 | 1.8406 | [5 empty] | 3.8406 | Y |  |  |  | 3.8406 | 0.096015 | H | 40 | 20 | 80 | 30 | 20 | 30 | 60 | 110 | 50 | 220
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2027/28 | August | 3.6271 | [6 empty] | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | H | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | H | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2029/30 | July | 0 | 53 | 0 | 0 | 231 | 231 | 0 | 0 | 0 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | July | 2031/32 | January | 0.64835 |  |  |  | 2.957 | 1.336 |  | 4.9413 |  |  |  |  | 4.9413 | 0.093233 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 37 | 18 | 3 | 221 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36.21% | 5.172% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  | 0.3 | 3.7 |  | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | H | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | June | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2025/26 | June | 2026/27 | May | 1.2731 | [6 empty] | 1.2731 | Y |  |  |  | 1.2731 | 0.10609 | M | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150
P48363 | Dover Heights - KHA | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | September | 23 | 17 | 6 | 0 | 91 | 71 | 20 | 0 | 17 | 2 | 10 | 3 | 2 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.09% | 0% | SR | D&B | 2027/28 | September | 2029/30 | April | 0 |  | 2.783 |  |  |  |  | 2.783 |  |  |  |  | 2.783 | 0.121 | M | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | May | 41 | 30 | 7 | 4 | 196 | 126 | 54 | 16 | 30 | 0 | 24 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.83% | 9.756% | SR | D&B | 2025/26 | June | 2027/28 | June | 3.8097 | [6 empty] | 3.8097 | Y |  | 0.8 | 0.0198 | 4.6295 | 0.11291 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | December | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | D&B | 2024/25 | January | 2026/27 | April | 3.1152 | [6 empty] | 3.1152 |  |  |  |  | 3.1152 | 0.097352 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 8 | 8 | 0 | 0 | 36 | 36 | 0 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | 0 |  |  |  | 0.83482 |  |  | 0.83482 |  |  |  |  | 0.83482 | 0.10435 | H | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P48338 | James Bank Hostel Redevelopment (Direct Access) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2026/27 | July | 11 | 11 | 0 | 0 | 22 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2027/28 | October | 0 | 1.111 | [5 empty] | 1.111 |  |  |  |  | 1.111 | 0.101 | H | 40 | 20 | 80 | 30 | 20 | 10 | 60 | 110 | 30 | 200
P46174 | James Bank Hostel Redevelopment (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2026/27 | July | 8 | 8 | 0 | 0 | 32 | 32 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | July | 2027/28 | October | 0 | 0.72 | [5 empty] | 0.72 |  |  |  |  | 0.72 | 0.09 | H | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240
P48429 | Masterton Farmhouse | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2025/26 | January | 4 | 4 | 0 | 0 | 16 | 16 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | January | 2026/27 | October | 0 | 0.41741 | [5 empty] | 0.41741 |  |  |  |  | 0.41741 | 0.10435 | M | 40 | 20 | 40 | 30 | 0 | 10 | 60 | 70 | 10 | 140
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2029/30 | February | 1.25 |  |  | 2.5915 |  |  |  | 3.8415 | Y |  | 0.75 |  | 4.5915 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 49 | 35 | 11 | 3 | 283 | 219 | 46 | 18 | 35 | 0 | 16 | 13 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 6.122% | SR | FC BS | 2027/28 | April | 2029/30 | February | 0.75 |  |  | 2.5633 | 0.6 |  |  | 3.9133 |  |  | 1.2 |  | 5.1133 | 0.10435 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48337 | Wellwood, Dunfermline | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | July | 35 | 24 | 9 | 2 | 162 | 116 | 38 | 8 | 24 | 0 | 10 | 8 | 6 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.43% | 5.714% | SR | D&B | 2026/27 | July | 2028/29 | July | 0 | 2.117 | 2.117 |  |  |  |  | 4.234 | Y |  |  |  | 4.234 | 0.12097 | H | 40 | 20 | 10 | 70 | 20 | 20 | 60 | 80 | 40 | 180
P48548 | Wester Whitefield (Halbeath SDA) (MMR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2026/27 | March | 33 | 33 | 0 | 0 | 136 | 136 | 0 | 0 | 33 | 0 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 1.7 |  |  |  |  | 2.7 |  |  |  |  | 2.7 | 0.081818 | H | 40 | 20 | 40 | 70 | 20 | 10 | 60 | 110 | 30 | 200
P48549 | Wester Whitefield (Halbeath SDA) (SR) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | March | 56 | 35 | 17 | 4 | 246 | 151 | 79 | 16 | 35 | 0 | 24 | 11 | 0 | 0 | 0 | 17 | 0 | 10 | 5 | 0 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 37.5% | 7.143% | SR | D&B | 2026/27 | March | 2029/30 | August | 0 | 1 | 6.26 |  |  |  |  | 7.26 |  |  |  |  | 7.26 | 0.12964 | H | 40 | 20 | 40 | 70 | 20 | 20 | 60 | 110 | 40 | 210
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December | 0 |  |  | 0.62612 |  |  |  | 0.62612 | Y |  |  |  | 0.62612 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | March | 56 | 42 | 10 | 4 | 308 | 228 | 64 | 16 | 42 | 0 | 4 | 16 | 22 | 0 | 0 | 10 | 0 | 4 | 0 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 25% | 7.143% | SR | D&B | 2025/26 | March | 2027/28 | March | 0 | 2.5 | 3.484 |  |  |  |  | 5.984 | Y |  | 0.9 |  | 6.884 | 0.12293 | H | 50 | 50 | 30 | 30 | 0 | 20 | 100 | 60 | 20 | 180
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | January | 19 | 13 | 5 | 1 | 85 | 61 | 20 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | February | 2026/27 | January | 0.5 | 1.3266 | [5 empty] | 1.8266 | Y |  | 0.4 |  | 2.2266 | 0.11719 | H | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | June | 10 | 8 | 2 | 0 | 45 | 37 | 8 | 0 | 8 | 0 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | SR | D&B | 2028/29 | November | 2028/29 | January | 0 |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.1176 | M | 30 | 35 | 10 | 10 | 0 | 10 | 65 | 20 | 10 | 95
P45414 | Open Market Purchases 26/27 | Fife | Fife |  | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March | 0 | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46084 | Open Market Purchases 27/28 | Fife | Fife |  | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March | 0 |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P46934 | Open Market Purchases 28/29 | Fife | Fife |  | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | 0 |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P47778 | Open Market Purchases 29/30 | Fife | Fife |  | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P48325 | Open Market Purchases 30/31 | Fife | Fife |  | No | FC | FC | 2030/31 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2030/31 | April | 2030/31 | March | 0 |  |  |  |  | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | May | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | May | 2028/29 | August | 0 | 1.2958 | 1 |  |  |  |  | 2.2958 | Y |  |  |  | 2.2958 | 0.10435 | M | 30 | 15 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 20 | 7 | 2 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2026/27 | April | 2027/28 | April | 0 | 1.4262 | 1.1 |  |  |  |  | 2.5262 | Y |  | 0.5 |  | 3.0262 | 0.10435 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P41471 | Glenwood Centre Regeneration (FC) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | October | 20 | 0 | 20 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.8256 | [5 empty] | 1.8256 | Y |  | 0.4 | 0.0493 | 2.2749 | 0.11374 | H | 50 | 25 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 9 | 9 | 0 | 0 | 88 | 88 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | September | 0.75 | 0.1 | [5 empty] | 0.85 | Y |  |  |  | 0.85 | 0.094444 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 15 | 15 | 0 | 0 | 88 | 88 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | October | 2027/28 | September | 1 | 0.855 | [5 empty] | 1.855 | Y |  |  |  | 1.855 | 0.12367 | H | 50 | 25 | 50 | 70 | 20 | 20 | 75 | 120 | 40 | 235
P48550 | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2028/29 | August | 30 | 0 | 22 | 8 | 67 | 0 | 49 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 17 | 5 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 100% | 26.67% | SR | D&B | 2028/29 | August | 2029/30 | August | 0 |  |  | 3.1306 |  |  |  | 3.1306 |  |  |  |  | 3.1306 | 0.10435 | H | 50 | 25 | 30 | 30 | 20 | 30 | 75 | 60 | 50 | 185
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | H | 50 | 25 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245
P48336 | Westwood Park Phase 2 MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2025/26 | October | 49 | 45 | 4 | 0 | 214 | 194 | 20 | 0 | 45 | 0 | 33 | 10 | 2 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.163% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | January | 2.26 | 1.621 | [5 empty] | 3.881 |  |  |  |  | 3.881 | 0.079204 | H | 50 | 25 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195
P48335 | Westwood Park Phase 2 SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | October | 31 | 22 | 9 | 0 | 152 | 110 | 42 | 0 | 22 | 0 | 8 | 6 | 8 | 0 | 0 | 9 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.03% | 0% | SR | D&B | 2025/26 | October | 2027/28 | January | 1.855 | 1.855 | [5 empty] | 3.71 |  |  |  |  | 3.71 | 0.11968 | H | 50 | 25 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 19 | 9 | 2 | 129 | 85 | 36 | 8 | 0 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  | 2.114 |  |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | M | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.31306 |  |  | 0.31306 | Y |  |  |  | 0.31306 | 0.10435 | H | 40 | 40 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190
P48147 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | September | 2027/28 | May | 0.2 | 0.91129 | [5 empty] | 1.1113 | Y |  |  |  | 1.1113 | 0.085484 | M | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120
P48146 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | August | 31 | 20 | 8 | 3 | 144 | 91 | 40 | 13 | 20 | 0 | 11 | 7 | 2 | 0 | 0 | 8 | 0 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.48% | 9.677% | SR | D&B | 2025/26 | September | 2027/28 | May | 2.5 | 0.55225 | [5 empty] | 3.0523 | Y |  | 0.6 |  | 3.6523 | 0.11781 | M | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 29 | 14 | 2 | 189 | 116 | 65 | 8 | 0 | 0 | 18 | 11 | 0 | 0 | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2029/30 | October | 2031/32 | March | 0 |  |  |  | 1 | 3.008 |  | 4.008 |  |  |  |  | 4.008 | 0.089067 | M | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 6 | 3 | 3 | 0 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | 0 |  |  |  | 0.2 | 0.388 |  | 0.588 |  |  |  |  | 0.588 | 0.098 | M | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 48 | 31 | 17 | 0 | 210 | 132 | 78 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 17 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.42% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0 |  |  | 2.351 | 2.351 |  |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | H | 50 | 45 | 0 | 70 | 0 | 10 | 95 | 70 | 10 | 175
P48430 | Leven Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | November | 14 | 10 | 3 | 1 | 64 | 48 | 12 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2027/28 | November | 2028/29 | June | 0 |  |  | 1.4609 |  |  |  | 1.4609 |  |  |  |  | 1.4609 | 0.10435 | H | 50 | 45 | 40 | 30 | 0 | 20 | 95 | 70 | 20 | 185
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 40 | 27 | 9 | 4 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2028/29 | November | 2030/31 | October | 0 |  |  | 2 | 2.1741 |  |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 26 | 10 | 4 | 178 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 35% | 10% | SR | D&B | 2029/30 | October | 2031/32 | October | 0 |  |  |  | 1 | 3.1741 |  | 4.1741 | Y |  |  |  | 4.1741 | 0.10435 | M | 40 | 40 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2025/26 | April | 25 | 23 | 0 | 2 | 98 | 92 | 0 | 6 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2025/26 | April | 2026/27 | June | 2.8235 | [6 empty] | 2.8235 | Y |  |  |  | 2.8235 | 0.11294 | H | 50 | 50 | 10 | 70 | 20 | 20 | 100 | 80 | 40 | 220
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2023/24 | April | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2026/27 | May | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | H | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2029/30 | September | 0 | 20 | 3 | 1 | 95 | 80 | 3 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16.67% | 4.167% | MMR 30 | D&B | 2029/30 | September | 2031/32 | April | 0 |  |  |  | 1.105 | 0.839 |  | 1.944 |  |  |  |  | 1.944 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160 | 24 units to be delivered | 24
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2030/31 | January | 0 | 35 | 13 | 2 | 227 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 4% | SR | D&B | 2030/31 | January | 2032/33 | December | 0 |  |  |  |  | 0.5 | 4.7176 | 5.2176 | Y |  |  |  | 5.2176 | 0.10435 | M | 50 | 50 | 10 | 10 | 20 | 20 | 100 | 20 | 40 | 160 | 50 units to be delivered | 50
P44715 | Kirkcaldy, Kingdom Park Phase 3 - FC | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 60 | 23 | 4 | 395 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 31.03% | 4.598% | SR | D&B | 2029/30 | January | 2032/33 | January | 0 |  |  |  | 1 | 4 | 3.4787 | 8.4787 | Y |  | 0.6 |  | 9.0787 | 0.10435 | H | 50 | 50 | 40 | 30 | 20 | 20 | 100 | 70 | 40 | 210 | 87 units to be delivered | 87
P46106 | Templehall Regeneration Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | September | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2028/29 | September | 2030/31 | August | 0 |  |  | 1.0522 |  |  |  | 1.0522 | Y |  | 0.2 |  | 1.2522 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P46177 | Templehall Regeneration Phase 4 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2028/29 | September | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | September | 2030/31 | November | 0 |  |  | 0.972 |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | M | 50 | 50 | 0 | 30 | 20 | 10 | 100 | 30 | 30 | 160
P48431 | Templehall Regerneration Phase 2 (OPH) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | September | 30 | 0 | 27 | 3 | 80 | 0 | 71 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 10 | 17 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 10% | SR | FC BS | 2026/27 | September | 2028/29 | August | 0 | 1 | 1.6306 |  |  |  |  | 2.6306 |  |  | 0.5 |  | 3.1306 | 0.10435 | H | 50 | 50 | 0 | 30 | 20 | 30 | 100 | 30 | 50 | 180
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 51 | 20 | 27 | 4 | 188 | 80 | 96 | 12 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 27 | 6 | 21 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 60.78% | 7.843% | SR | D&B | 2027/28 | April | 2028/29 | May | 0 |  | 2.5 | 2.1573 |  |  |  | 4.6573 | Y |  | 1 |  | 5.6573 | 0.11093 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 30 | 30 | 0 | 0 | 86 | 86 | 0 | 0 | 30 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 1.5 | 0.93 |  |  |  | 2.43 |  |  |  |  | 2.43 | 0.081 | H | 50 | 50 | 0 | 30 | 20 | 20 | 100 | 30 | 40 | 170
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 53 | 45 | 8 | 0 | 176 | 150 | 26 | 0 | 45 | 15 | 30 | 0 | 0 | 0 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.09% | 0% | SR | D&B | 2027/28 | October | 2029/30 | March | 0 |  | 2 | 3.883 |  |  |  | 5.883 |  |  |  |  | 5.883 | 0.111 | H | 50 | 50 | 0 | 70 | 20 | 20 | 100 | 70 | 40 | 210
P48432 | Viewforth Terrace | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2026/27 | December | 25 | 17 | 6 | 2 | 118 | 81 | 29 | 8 | 17 | 0 | 8 | 5 | 4 | 0 | 0 | 6 | 0 | 4 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2026/27 | August | 2027/28 | April | 0 | 1.5 | 0.60882 |  |  |  |  | 2.1088 |  |  | 0.5 |  | 2.6088 | 0.10435 | M | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 46 | 31 | 15 | 0 | 196 | 132 | 64 | 0 | 31 | 0 | 23 | 8 | 0 | 0 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.61% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  | 3.1564 |  |  |  | 4.6042 |  |  |  |  | 4.6042 | 0.10009 | H | 30 | 5 | 50 | 70 | 0 | 20 | 35 | 120 | 20 | 175
P45421 | Park Drive (RHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2026/27 | April | 2027/28 | January | 0.387 | 2.1294 | [5 empty] | 2.5164 | Y |  | 0.5 | 0.0098 | 3.0262 | 0.10435 | H | 50 | 45 | 50 | 30 | 20 | 20 | 95 | 80 | 40 | 215
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | January | 45 | 31 | 14 | 0 | 163 | 114 | 49 | 0 | 31 | 6 | 21 | 4 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.11% | 0% | SR | D&B | 2025/26 | January | 2027/28 | August | 1.9093 | 2.962 | [5 empty] | 4.8713 | Y |  |  |  | 4.8713 | 0.10825 | H | 40 | 10 | 80 | 70 | 20 | 10 | 50 | 150 | 30 | 230
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | November | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | H | 40 | 10 | 80 | 70 | 0 | 30 | 50 | 150 | 30 | 230
P48433 | Jenny Gray Phase 2 ( Former Wilson Bruce Court) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 10 | 7 | 2 | 1 | 43 | 31 | 8 | 4 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2029/30 | April | 2030/31 | April | 0 |  |  |  | 1.0435 |  |  | 1.0435 |  |  |  |  | 1.0435 | 0.10435 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2027/28 | August | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | H | 40 | 10 | 80 | 70 | 0 | 20 | 50 | 150 | 20 | 220
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2028/29 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2028/29 | August | 2030/31 | May | 0 |  |  | 1.5 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | M | 40 | 10 | 50 | 30 | 20 | 10 | 50 | 80 | 30 | 160
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2029/30 | April | 0 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2029/30 | April | 2031/32 | February | 0 |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | M | 30 | 35 | 10 | 30 | 0 | 20 | 65 | 40 | 20 | 125 | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 20 | 13 | 6 | 1 | 95 | 59 | 32 | 4 | 13 | 0 | 6 | 7 | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | D&B | 2028/29 | January | 2030/31 | June | 0 |  |  | 0.25 | 1.709 |  |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | M | 40 | 10 | 0 | 30 | 0 | 20 | 50 | 30 | 20 | 100
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2027/28 | August | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | H | 40 | 10 | 80 | 70 | 20 | 20 | 50 | 150 | 40 | 240
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June | 0 |  | 2.602 |  |  |  |  | 2.602 | Y |  |  |  | 2.602 | 0.10408 | M | 50 | 25 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105
P45416 | Methilhaven Road (Prev. Care Home )(or Alternative Site) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2028/29 | April | 2029/30 | January | 0 |  |  | 2 | 2.174 |  |  | 4.174 | Y |  |  |  | 4.174 | 0.10435 | H | 50 | 45 | 50 | 10 | 20 | 20 | 95 | 60 | 40 | 195
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2028/29 | November | 4 | 2 | 2 | 0 | 16 | 8 | 8 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2028/29 | November | 2029/30 | July | 0 |  |  | 0.468 |  |  |  | 0.468 |  |  |  |  | 0.468 | 0.117 | H | 50 | 25 | 10 | 70 | 0 | 20 | 75 | 80 | 20 | 175
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | M | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145
P48551 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KI | 2027/28 | October | 6 | 6 | 0 | 0 | 26 | 24 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2028/29 | October | 0 |  | 0.702 |  |  |  |  | 0.702 | Y |  |  |  | 0.702 | 0.117 | M | 30 | 35 | 0 | 70 | 0 | 20 | 65 | 70 | 20 | 155
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 38 | 27 | 9 | 2 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.2 | 3.524 |  | 3.724 |  |  |  |  | 3.724 | 0.098 | M | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160
P48552 | Castle Road | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2030/31 | July | 0 | 6 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2030/31 | July | 2031/32 | March | 0 |  |  |  |  | 0.54 |  | 0.54 |  |  |  |  | 0.54 | 0.09 | L | 40 | 20 | 10 | 10 | 0 | 10 | 60 | 20 | 10 | 90 | 6 units to be delivered | 6
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2026/27 | April | 30 | 24 | 4 | 2 | 158 | 122 | 28 | 8 | 24 | 0 | 4 | 8 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 20% | 6.667% | SR | D&B | 2026/27 | April | 2027/28 | September | 0.41 | 1 | 1.2206 |  |  |  |  | 2.6306 | Y |  | 0.5 |  | 3.1306 | 0.10435 | H | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | April | 36 | 24 | 10 | 2 | 166 | 112 | 46 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2026/27 | April | 2027/28 | December | 0 | 2 | 1.5436 |  |  |  |  | 3.5436 |  |  | 0.6 |  | 4.1436 | 0.1151 | H | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 25 | 18 | 6 | 1 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2029/30 | August | 2030/31 | August | 0 |  |  |  | 0.3 | 2.15 |  | 2.45 |  |  |  |  | 2.45 | 0.098 | M | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2030/31 | December | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2030/31 | April | 0 | 28 | 10 | 2 | 214 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2030/31 | June | 2031/32 | March | 0 |  |  |  |  | 0.78996 | 3 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | M | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | 40 units to be delivered | 40
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2025/26 | May | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | June | 0.752 | [6 empty] | 0.752 |  |  |  |  | 0.752 | 0.083556 | H | 30 | 5 | 90 | 70 | 20 | 10 | 35 | 160 | 30 | 225
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2025/26 | May | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2025/26 | May | 2026/27 | June | 2.212 | [6 empty] | 2.212 |  |  |  |  | 2.212 | 0.11642 | H | 30 | 5 | 90 | 70 | 20 | 20 | 35 | 160 | 40 | 235
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | February | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | March | 2026/27 | June | 2.4601 | [6 empty] | 2.4601 | Y |  | 1 | 0.0396 | 3.4997 | 0.11666 | H | 30 | 5 | 80 | 70 | 0 | 20 | 35 | 150 | 20 | 205
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 0 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2030/31 | January | 2031/32 | January | 0.34619 |  |  |  |  | 0.3 | 0.815 | 1.4612 | Y |  |  |  | 1.4612 | 0.10437 | M | 20 | 30 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | 14 units to be delivered | 14
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | 0 |  |  | 0.20871 |  |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | M | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 35 | 12 | 3 | 240 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 6% | SR | D&B | 2029/30 | January | 2031/32 | March | 0 |  |  |  | 2.1176 | 1.9 |  | 4.0176 | Y |  | 1.2 |  | 5.2176 | 0.10435 | M | 50 | 25 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | 0 |  |  |  | 0.20871 |  |  | 0.20871 | Y |  |  |  | 0.20871 | 0.10435 | H | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March | 0 | 0.784 | [5 empty] | 0.784 | Y |  |  |  | 0.784 | 0.098 | H | 50 | 45 | 30 | 70 | 0 | 10 | 95 | 100 | 10 | 205
[10 empty] | 2640 | 2319 | 850 | 214 | 14581 | 10247 | 3482 | 850 | 1797 | 91 | 1137 | 881 | 208 | 2 | 0 | 668 | 136 | 540 | 59 | 38 | 75 | 2 | 175 | 21 | 163 | 30 | 0 | 0 | 0 | 40.3% | 8.106% | [6 empty] | 79.1784 | 45.2362 | 46.839 | 44.8731 | 41.838 | 41.7394 | 14.0114 | 313.7155 |  | 0 | 19.7 | 0.4732 | 333.8887
|  |  |  | Total Potential Units Delivered during SHIP 2026/27-2030/31 | [5 empty] | 124 | 141 | 47 | 21 |  | 657 | 272 | 89 |  | 0 | 77 | 45 | 19 | 0 | 0 |  | 0 | 34 | 4 | 1 | 8 | 0