## SHIP WD
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2024/25 - 2028/29)
SHIP Projects Table
HARP Ref | Project Name | Town | LHS Area | HMA | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Units Check | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 224/25 | SG Grant 2024/2025 (£m) | SG Grant 2025/2026 (£m) | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant Post 2028/2029 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equalities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Priority (LMH) | Comments
P46103 | Hillside School | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | FC PSD | FC | 2026/27 | December | 38 | 26 | 6 | 6 | 38 | 180 | 122 | 32 | 26 | 26 | 0 | 12 | 10 | 4 | 0 | 0 | 6 | 0 | 2 | 2 | 0 | 2 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 31.58% | 15.79% | SR | D&B | 2026/27 | December | 2027/28 | March |  |  |  | 1 | 2.6 |  |  | 3.6 |  |  |  | 3.6 | 0.094738 | 40 | 35 | 0 | 30 | 0 | 20 | 75 | 30 | 20 | 125 | M
P43211 | Main Street | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2025/26 | January | 21 | 15 | 6 | 0 | 21 | 93 | 69 | 24 | 0 | 15 | 0 | 6 | 9 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2025/26 | January | 2027/28 | June |  |  | 0.1 | 1.957 |  |  |  | 2.057 |  |  |  | 2.057 | 0.097952 | 40 | 35 | 40 | 30 | 0 | 10 | 75 | 70 | 10 | 155 | M
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | FC | FC | 2026/27 | September | 20 | 14 | 4 | 2 | 20 | 45 | 31 | 10 | 4 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | September | 2027/28 | December |  |  |  | 1 | 1.895 |  |  | 2.895 | Y |  |  | 2.895 | 0.14475 | 30 | 45 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195 | H
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | FC | FC | 2024/25 | January | 14 | 0 | 10 | 4 | 14 | 41 | 0 | 25 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 100% | 28.57% | SR | D&B | 2024/25 | January | 2025/26 | December |  | 0.32649 | 1 |  |  |  |  | 1.3265 | Y |  |  | 1.3265 | 0.094749 | 30 | 45 | 50 | 30 | 20 | 30 | 75 | 80 | 50 | 205 | H
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | KHA | KHA | 2025/26 | March | 30 | 19 | 10 | 1 | 30 | 122 | 76 | 42 | 4 | 19 | 0 | 14 | 5 | 0 | 0 | 0 | 10 | 0 | 9 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2025/26 | March | 2027/28 | November |  |  | 0.6 | 1.169 | 1.169 |  |  | 2.938 |  |  |  | 2.938 | 0.097933 | 20 | 10 | 0 | 10 | 0 | 10 | 30 | 10 | 10 | 50 | L
P46187 | Stratheden Place | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | KHA | KHA | 2023/24 | April | 4 | 2 | 0 | 2 | 4 | 18 | 10 | 0 | 8 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 50% | 50% | SR | D&B | 2023/24 | June | 2023/24 | November | 0.374 | [6 empty] | 0.374 | Y |  |  | 0.374 | 0.0935 | 20 | 10 | 40 | 70 | 0 | 20 | 30 | 110 | 20 | 160 | M
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | KHA | KHA | 2028/29 | January | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 89 | 27 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March | [5 empty] | 0.5 | 3.418 | 3.918 |  |  |  | 3.918 | 0.09795 | 40 | 25 | 0 | 10 | 0 | 10 | 65 | 10 | 10 | 85 | M | 40 units to be delivered | 40
P41440 | Main Street | Balmullo | St Andrews | St Andrews & East Fife | KHA | KHA | 2023/24 | March | 19 | 16 | 2 | 1 | 19 | 78 | 60 | 14 | 4 | 16 | 0 | 9 | 6 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 15.79% | 5.263% | SR | D&B | 2023/24 | March | 2025/26 | June | 0.1 | 1.761 | [5 empty] | 1.861 |  |  |  | 1.861 | 0.097947 | 30 | 5 | 10 | 30 | 0 | 10 | 35 | 40 | 10 | 85 | M
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | FC PSD | FC | 2024/25 | January | 15 | 11 | 3 | 1 | 15 | 154 | 80 | 70 | 4 | 11 | 0 | 5 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2024/25 | January | 2026/27 | October |  |  | 1.0212 |  |  |  |  | 1.0212 | Y | 0.4 |  | 1.4212 | 0.094749 | 40 | 20 | 0 | 10 | 0 | 20 | 60 | 10 | 20 | 90 | M
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | FC | FC | 2024/25 | September | 18 | 13 | 4 | 1 | 18 | 86 | 62 | 20 | 4 | 13 | 0 | 6 | 4 | 3 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | September | 2025/26 | September |  | 0.3 | 1.3573 |  |  |  |  | 1.6573 | Y |  | 0.048167 | 1.7055 | 0.094749 | 40 | 20 | 10 | 30 | 0 | 20 | 60 | 40 | 20 | 120 | M
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | KHA | KHA | 2024/25 | January | 63 | 45 | 11 | 7 | 63 | 291 | 204 | 56 | 31 | 45 | 0 | 27 | 15 | 3 | 0 | 0 | 11 | 0 | 8 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 28.57% | 11.11% | SR | D&B | 2024/25 | January | 2027/28 | November |  | 0.5 | 2 | 2 | 1.671 |  |  | 6.171 | Y |  |  | 6.171 | 0.097952 | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180 | H
P41362 | Dundonald Farm (OTS) | Cardenden | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2027/28 | March | 12 | 11 | 0 | 1 | 12 | 53 | 48 | 0 | 5 | 11 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 8.333% | 8.333% | SR | OTS | 2027/28 | March | 2028/29 | March | [5 empty] | 1.137 |  | 1.137 |  |  |  | 1.137 | 0.094749 | 50 | 40 | 0 | 10 | 0 | 10 | 90 | 10 | 10 | 110 | M
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | KHA | KHA | 2027/28 | July | 30 | 19 | 10 | 1 | 30 | 122 | 76 | 42 | 4 | 19 | 0 | 14 | 5 | 0 | 0 | 0 | 10 | 0 | 9 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2027/28 | July | 2028/29 | March | 0.314 |  |  |  | 1.938 | 1 |  | 3.252 |  |  |  | 3.252 | 0.1084 | 40 | 20 | 50 | 30 | 0 | 10 | 60 | 80 | 10 | 150 | M
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2024/25 | January | 10 | 10 | 0 | 0 | 10 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2024/25 | January | 2025/26 | March |  | 0.49 | 0.49 |  |  |  |  | 0.98 |  |  |  | 0.98 | 0.098 | 50 | 30 | 10 | 30 | 0 | 10 | 80 | 40 | 10 | 130 | M
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | KHA | KHA | 2024/25 | October | 15 | 11 | 0 | 4 | 15 | 67 | 51 | 0 | 16 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 26.67% | 26.67% | SR | D&B | 2024/25 | October | 2025/26 | March |  | 0.5 | 0.954 |  |  |  |  | 1.454 |  |  |  | 1.454 | 0.096933 | 30 | 45 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125 | M
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | KHA | OVHA | 2025/26 | September | 29 | 29 | 0 | 0 | 29 | 105 | 105 | 0 | 0 | 29 | 12 | 4 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | September | 2026/27 | October | 0 |  | 1 | 1.841 |  |  |  | 2.841 | Y |  |  | 2.841 | 0.097966 | 40 | 25 | 0 | 30 | 20 | 10 | 65 | 30 | 30 | 125 | M
P41381 | Valley House, Hill Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | FC | FC | 2021/22 | January | 19 | 12 | 6 | 1 | 19 | 94 | 58 | 32 | 4 | 12 | 0 | 6 | 4 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 36.84% | 5.263% | SR | D&B | 2023/24 | December | 2025/26 | July | 1.1789 | [6 empty] | 1.1789 | Y | 0.5 |  | 1.6789 | 0.088364 | 40 | 25 | 80 | 70 | 0 | 20 | 65 | 150 | 20 | 235 | H
P44074 | Ordnance Road | Crombie | West Fife Villages | Dunfermline & West Fife | FC PSD | FC | 2023/24 | September | 19 | 14 | 5 | 0 | 19 | 88 | 68 | 20 | 0 | 14 | 0 | 4 | 8 | 2 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.32% | 0% | SR | D&B | 2023/24 | September | 2024/25 | September | 1 | 0.21139 | [5 empty] | 1.2114 | Y | 0.5 |  | 1.7114 | 0.090073 | 40 | 20 | 30 | 70 | 0 | 20 | 60 | 100 | 20 | 180 | H
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2025/26 | January | 53 | 35 | 17 | 1 | 53 | 216 | 140 | 72 | 4 | 35 | 0 | 27 | 8 | 0 | 0 | 0 | 17 | 0 | 15 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.96% | 1.887% | SR | D&B | 2025/26 | January | 2028/29 | March |  |  | 0.833 | 2 | 1.834 |  |  | 4.667 |  |  |  | 4.667 | 0.088057 | 40 | 35 | 40 | 70 | 0 | 10 | 75 | 110 | 10 | 195 | H
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | FC PSD | FC | 2026/27 | June | 13 | 8 | 4 | 1 | 13 | 51 | 31 | 16 | 4 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 38.46% | 7.692% | SR | D&B | 2026/27 | June | 2027/28 | November |  |  |  | 0.932 |  |  |  | 0.932 | Y | 0.3 |  | 1.232 | 0.094769 | 40 | 25 | 0 | 10 | 0 | 20 | 65 | 10 | 20 | 95 | M
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | FC | FC | 2027/28 | October | 4 | 0 | 0 | 4 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2027/28 | October | 2028/29 | May |  |  |  |  | 0.379 |  |  | 0.379 | Y |  |  | 0.379 | 0.094749 | 40 | 25 | 50 | 10 | 20 | 30 | 65 | 60 | 50 | 175 | H
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | KHA | KHA | 2025/26 | April | 25 | 17 | 8 | 0 | 25 | 106 | 72 | 34 | 0 | 17 | 0 | 13 | 4 | 0 | 0 | 0 | 8 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | SR | D&B | 2025/26 | April | 2026/27 | March |  |  | 1.224 | 1.224 |  |  |  | 2.448 |  |  |  | 2.448 | 0.09792 | 20 | 10 | 10 | 30 | 20 | 10 | 30 | 40 | 30 | 100 | M
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | KHA | KI | 2025/26 | April | 6 | 6 | 0 | 0 | 6 | 24 | 12 | 12 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | April | 2026/27 | March |  |  | 0.416 |  |  |  |  | 0.416 |  |  |  | 0.416 | 0.069333 | 20 | 10 | 10 | 30 | 20 | 10 | 30 | 40 | 30 | 100 | M
P44702 | Dalgairn (New Care Village) | Cupar | Cupar & HOF | Cupar & North West Fife | FC | FC | 2024/25 | April | 12 | 0 | 12 | 0 | 12 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2024/25 | April | 2025/26 | October | 1.0478 | [6 empty] | 1.0478 | Y |  | 0.0331 | 1.0809 | 0.090073 | 20 | 10 | 50 | 70 | 20 | 30 | 30 | 120 | 50 | 200 | H
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | KHA | KHA | 2025/26 | April | 13 | 6 | 7 | 0 | 13 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2025/26 | April | 2027/28 | March |  |  | 1.274 |  |  |  |  | 1.274 | Y |  |  | 1.274 | 0.098 | 20 | 10 | 10 | 30 | 0 | 10 | 30 | 40 | 10 | 80 | M
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | KHA | KI | 2027/28 | June | 12 | 12 | 0 | 0 | 12 | 54 | 54 | 0 | 0 | 12 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | June | 2028/29 | February |  |  |  |  | 0.832 |  |  | 0.832 |  |  |  | 0.832 | 0.069333 | 20 | 10 | 10 | 30 | 0 | 10 | 30 | 40 | 10 | 80 | M
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | KHA | KHA | 2026/27 | June | 38 | 25 | 13 | 0 | 38 | 165 | 106 | 59 | 0 | 25 | 0 | 19 | 6 | 0 | 0 | 0 | 13 | 0 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.21% | 0% | SR | D&B | 2026/27 | June | 2028/29 | February |  |  |  | 1.882 | 1.841 |  |  | 3.723 |  |  |  | 3.723 | 0.097974 | 20 | 10 | 10 | 30 | 0 | 10 | 30 | 40 | 10 | 80 | M
P44735 | Inner Court (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | KHA | KI | 2023/24 | March | 13 | 13 | 0 | 0 | 13 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2023/24 | March | 2025/26 | June | 0.1 | 0.801 | [5 empty] | 0.901 | Y |  | 0.0132 | 0.9142 | 0.070323 | 20 | 10 | 80 | 70 | 20 | 10 | 30 | 150 | 30 | 210 | H
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | FC PSD | FC | 2023/24 | March | 10 | 10 | 0 | 0 | 10 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2024/25 | April | 2026/27 | April | 0.1 | 0.54749 | [5 empty] | 0.64749 | Y | 0.3 |  | 0.94749 | 0.094749 | 20 | 10 | 30 | 70 | 20 | 10 | 30 | 100 | 30 | 160 | M
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | FC | FC | 2025/26 | March | 20 | 14 | 4 | 2 | 20 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2025/26 | March | 2027/28 | April |  |  |  | 1.895 |  |  |  | 1.895 | Y |  |  | 1.895 | 0.094749 | 20 | 10 | 50 | 30 | 20 | 20 | 30 | 80 | 40 | 150 | M
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | KHA | KHA | 2023/24 | October | 49 | 34 | 12 | 3 | 49 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2023/24 | October | 2025/26 | April | 3.0982 | 1.702 | [5 empty] | 4.8002 | Y |  |  | 4.8002 | 0.097963 | 20 | 10 | 50 | 30 | 0 | 20 | 30 | 80 | 20 | 130 | M
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | KHA | KHA | 2025/26 | December | 20 | 14 | 6 | 0 | 20 | 84 | 56 | 28 | 0 | 14 | 0 | 6 | 8 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | SR | D&B | 2025/26 | December | 2026/27 | March |  |  | 0.8 | 1.159 |  |  |  | 1.959 | Y |  |  | 1.959 | 0.09795 | 20 | 10 | 0 | 30 | 0 | 10 | 30 | 30 | 10 | 70 | L
P46448 | Fulmar Way | Dalgety Bay | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2026/27 | April | 9 | 7 | 2 | 0 | 9 | 38 | 30 | 8 | 0 | 7 | 0 | 5 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.22% | 0% | SR | D&B | 2026/27 | April | 2027/28 | April |  |  |  | 0.882 |  |  |  | 0.882 | Y |  |  | 0.882 | 0.098 | 40 | 35 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125 | M
P41461 | Aberdour Road (Former Pitcorthie PS) (EC) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2021/22 | February | 33 | 0 | 31 | 2 | 33 | 110 | 0 | 102 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 11 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 6.061% | SR | D&B | 2023/24 | June | 2024/25 | February | 2.6198 | [6 empty] | 2.6198 | Y |  |  | 2.6198 | 0.079387 | 40 | 35 | 80 | 70 | 20 | 30 | 75 | 150 | 50 | 275 | H
P46874 | Aberdour Road / Evershed Drive (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC PSD | FC | 2024/25 | April | 40 | 0 | 27 | 13 | 40 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2024/25 | April | 2025/26 | March |  | 0.75 | 3.04 |  |  |  |  | 3.79 | Y |  |  | 3.79 | 0.094749 | 40 | 35 | 0 | 30 | 0 | 30 | 75 | 30 | 30 | 135 | M
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 45 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2024/25 | June | 3.6271 | [6 empty] | 3.6271 | Y |  | 0.20525 | 3.8323 | 0.085163 | 40 | 35 | 80 | 70 | 20 | 30 | 75 | 150 | 50 | 275 | H
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 85 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | November | 2025/26 | February | 3.4909 | 2 | 2.1737 |  |  |  |  | 7.6645 | Y |  |  | 7.6645 | 0.090171 | 40 | 35 | 80 | 70 | 0 | 10 | 75 | 150 | 10 | 235 | H
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | KHA | KI | 2024/25 | July | 53 | 53 | 0 | 0 | 53 | 231 | 231 | 0 | 0 | 53 | 8 | 34 | 8 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2024/25 | July | 2026/27 | January | 0.64835 | 1.5 | 1.336 |  |  |  |  | 3.4843 |  |  |  | 3.4843 | 0.065742 | 40 | 35 | 60 | 70 | 20 | 20 | 75 | 130 | 40 | 245 | H
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2026/27 | November | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 61 | 13 | 0 | 8 | 18 | 9 | 2 | 0 | 0 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | November | 2029/30 | October | 0.69637 |  |  | 0.75 | 2.206 | 2 |  | 5.6524 |  |  |  | 5.6524 | 0.097455 | 40 | 35 | 60 | 70 | 20 | 20 | 75 | 130 | 40 | 245 | H | 58 units to be delivered | 58
P46104 | Broomhall SLA, Future Phases | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2028/29 | June | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 71 | 8 | 0 | 0 | 25 | 8 | 0 | 0 | 0 | 0 | 0 | 11 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | June | 2029/30 | March | [5 empty] | 0.5 | 4.237 | 4.737 | Y |  |  | 4.737 | 0.09474 | 40 | 35 | 10 | 10 | 20 | 20 | 75 | 20 | 40 | 135 | M | 50 units to be delivered | 50
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC PSD | FC | 2024/25 | April | 42 | 30 | 9 | 3 | 42 | 185 | 124 | 48 | 13 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 9 | 0 | 5 | 0 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.57% | 7.143% | SR | D&B | 2023/24 | October | 2025/26 | September | 1.2 | 0.5 | 1.2795 |  |  |  |  | 2.9795 | Y | 1 |  | 3.9795 | 0.094749 | 40 | 35 | 0 | 30 | 20 | 20 | 75 | 30 | 40 | 145 | M
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2024/25 | September | 9 | 6 | 2 | 1 | 9 | 42 | 28 | 10 | 4 | 6 | 0 | 3 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 11.11% | SR | D&B | 2024/25 | September | 2025/26 | May |  | 0.76274 | [5 empty] | 0.76274 |  |  | 0.09 | 0.85274 | 0.094749 | 40 | 35 | 50 | 30 | 20 | 20 | 75 | 80 | 40 | 195 | H
P46174 | James Bank Hostel Redevelopment | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2023/24 | January | 19 | 19 | 0 | 0 | 19 | 76 | 76 | 0 | 0 | 19 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2023/24 | February | 2024/25 | March | 0.5 | 0.811 | [5 empty] | 1.311 |  |  |  | 1.311 | 0.069 | 40 | 35 | 50 | 70 | 20 | 10 | 75 | 120 | 30 | 225 | H
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2024/25 | January | 44 | 0 | 40 | 4 | 44 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2024/25 | January | 2026/27 | June | 1.25 | 0.1 | 1.5 | 0.36896 |  |  |  | 3.219 | Y | 0.95 |  | 4.169 | 0.094749 | 40 | 35 | 50 | 30 | 0 | 30 | 75 | 80 | 30 | 185 | H
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2025/26 | April | 45 | 31 | 11 | 3 | 45 | 265 | 201 | 46 | 18 | 31 | 0 | 14 | 11 | 6 | 0 | 0 | 11 | 0 | 4 | 3 | 2 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 31.11% | 6.667% | SR | FC BS | 2025/26 | April | 2026/27 | September | 0.75 |  | 1 | 1.7137 |  |  |  | 3.4637 |  | 0.8 |  | 4.2637 | 0.094749 | 40 | 35 | 50 | 30 | 0 | 20 | 75 | 80 | 20 | 175 | H
P41459 | Rumblingwell (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC PSD | FC | 2024/25 | October | 12 | 10 | 2 | 0 | 12 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2024/25 | October | 2025/26 | October |  | 0.4 | 0.73699 |  |  |  |  | 1.137 | Y |  |  | 1.137 | 0.094749 | 40 | 35 | 30 | 30 | 20 | 10 | 75 | 60 | 30 | 165 | M
P45410 | South Castle Drive | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | KHA | KI | 2026/27 | August | 18 | 18 | 0 | 0 | 18 | 72 | 72 | 0 | 0 | 18 | 0 | 17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | September | 2027/28 | October |  |  |  | 1.248 |  |  |  | 1.248 |  |  |  | 1.248 | 0.069333 | 40 | 35 | 0 | 10 | 0 | 10 | 75 | 10 | 10 | 95 | M
P47094 | Townhill Road (DUN038) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2023/24 | October | 16 | 11 | 4 | 1 | 16 | 75 | 51 | 20 | 4 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.25% | 6.25% | SR | D&B | 2023/24 | October | 2024/25 | March | 0.6 | 0.967 | [5 empty] | 1.567 | Y |  |  | 1.567 | 0.097937 | 40 | 35 | 40 | 70 | 0 | 20 | 75 | 110 | 20 | 205 | H
P46875 | Walmer Drive | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC PSD | FC | 2024/25 | April | 26 | 26 | 0 | 0 | 26 | 70 | 70 | 0 | 0 | 26 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2024/25 | April | 2025/26 | August |  | 1.2 | 0.86347 |  |  |  |  | 2.0635 |  | 0.4 |  | 2.4635 | 0.094749 | 40 | 35 | 10 | 30 | 20 | 10 | 75 | 40 | 30 | 145 | M
P43286 | Wester Whitefield (Halbeath SDA) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC PSD | FC | 2026/27 | July | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 89 | 17 | 0 | 0 | 30 | 30 | 9 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 2 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | July | 2029/30 | April |  |  |  | 1 | 2 | 2.4 | 3.2302 | 8.6302 | Y | 0.75 |  | 9.3802 | 0.094749 | 40 | 35 | 10 | 30 | 20 | 20 | 75 | 40 | 40 | 155 | M | 99 units to be delivered | 99
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2028/29 | May | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | June | 2029/30 | December | [5 empty] | 0.56849 |  | 0.56849 | Y |  |  | 0.56849 | 0.094749 | 40 | 35 | 50 | 10 | 20 | 30 | 75 | 60 | 50 | 185 | H | 6 units to be delivered | 6
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2025/26 | July | 34 | 24 | 10 | 0 | 34 | 170 | 122 | 48 | 0 | 24 | 0 | 10 | 2 | 12 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.41% | 0% | SR | D&B | 2025/26 | July | 2026/27 | March |  |  |  | 1.2 | 1.2625 |  |  | 2.4625 | Y | 0.6 |  | 3.0625 | 0.090073 | 50 | 40 | 30 | 70 | 0 | 20 | 90 | 100 | 20 | 210 | H
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC | FC | 2026/27 | April | 24 | 17 | 6 | 1 | 24 | 120 | 88 | 28 | 4 | 17 | 0 | 7 | 6 | 4 | 0 | 0 | 6 | 0 | 5 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 29.17% | 4.167% | SR | D&B | 2026/27 | April | 2027/28 | April |  |  |  | 1.774 |  |  |  | 1.774 | Y | 0.5 |  | 2.274 | 0.094749 | 50 | 40 | 50 | 30 | 20 | 20 | 90 | 80 | 40 | 210 | H
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | KHA | KHA | 2025/26 | June | 12 | 6 | 6 | 0 | 12 | 48 | 24 | 24 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2025/26 | November | 2026/27 | January |  |  | 0.588 | 0.588 |  |  |  | 1.176 |  |  |  | 1.176 | 0.098 | 30 | 45 | 10 | 10 | 0 | 10 | 75 | 20 | 10 | 105 | M
P43376 | Open Market Transactions 24/25 | Fife | Fife |  | FC | FC | 2024/25 | April | 50 | 50 | 0 | 0 | 50 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2024/25 | April | 2024/25 | March |  | 2 | [5 empty] | 2 |  |  |  | 2 | 0.04 | [6 empty] | 0 | 0 | 0 | 0 | H
P44705 | Open Market Transactions 25/26 | Fife | Fife |  | FC | FC | 2025/26 | April | 50 | 50 | 0 | 0 | 50 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2025/26 | April | 2025/26 | March |  |  | 2 |  |  |  |  | 2 |  |  |  | 2 | 0.04 | [6 empty] | 0 | 0 | 0 | 0 | H
P45414 | Open Market Transactions 26/27 | Fife | Fife |  | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 50 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March |  |  |  | 2 |  |  |  | 2 |  |  |  | 2 | 0.04 | [6 empty] | 0 | 0 | 0 | 0 | H
P46084 | Open Market Transactions 27/28 | Fife | Fife |  | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 50 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March |  |  |  |  | 2 |  |  | 2 |  |  |  | 2 | 0.04 | [6 empty] | 0 | 0 | 0 | 0 | H
P46934 | Open Market Transactions 28/29 | Fife | Fife |  | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 50 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March | [5 empty] | 2 |  | 2 |  |  |  | 2 | 0.04 | [6 empty] | 0 | 0 | 0 | 0 | H
P45420 | Main Road (EC Housing) | Gauldry | Tay Coast | Greater Dundee | FC | FC | 2024/25 | April | 22 | 0 | 20 | 2 | 22 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2024/25 | April | 2025/26 | December |  | 0.75 | 1.2977 |  |  |  |  | 2.0477 | Y |  |  | 2.0477 | 0.093078 | 30 | 15 | 0 | 30 | 0 | 30 | 45 | 30 | 30 | 105 | M
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC | FC | 2024/25 | March | 29 | 20 | 7 | 2 | 29 | 137 | 96 | 33 | 8 | 20 | 0 | 8 | 8 | 4 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.03% | 6.897% | SR | D&B | 2024/25 | March | 2026/27 | September |  |  | 1.8 | 0.94772 |  |  |  | 2.7477 | Y |  |  | 2.7477 | 0.094749 | 50 | 30 | 50 | 30 | 20 | 20 | 80 | 80 | 40 | 200 | H
P40203 | Detroit Road | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC | FC | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 47 | 32 | 0 | 0 | 15 | 14 | 3 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2030/31 | June | [5 empty] | 0.5 | 3.7637 | 4.2637 | Y |  |  | 4.2637 | 0.094749 | 50 | 30 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | M | 45 units to be delivered | 45
P41471 | Glenwood Centre Regeneration (FC) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC | FC | 2025/26 | April | 15 | 10 | 4 | 1 | 15 | 68 | 48 | 16 | 4 | 10 | 0 | 4 | 4 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2025/26 | April | 2026/27 | March |  |  | 1.0212 |  |  |  |  | 1.0212 | Y | 0.4 |  | 1.4212 | 0.094749 | 50 | 30 | 50 | 10 | 20 | 20 | 80 | 60 | 40 | 180 | H
P46175 | Glenwood Centre Regeneration (KHA) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2025/26 | April | 15 | 15 | 0 | 0 | 15 | 60 | 60 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | April | 2026/27 | March |  |  | 0.5 | 0.5 |  |  |  | 1 | Y |  |  | 1 | 0.066667 | 50 | 30 | 50 | 30 | 20 | 10 | 80 | 80 | 30 | 190 | H
P46876 | Leven Mill, Queensgate (OTS) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2023/24 | September | 17 | 17 | 0 | 0 | 17 | 70 | 70 | 0 | 0 | 17 | 0 | 6 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2023/24 | September | 2024/25 | October |  | 1.703 | [5 empty] | 1.703 | Y |  |  | 1.703 | 0.10018 | 50 | 30 | 30 | 30 | 0 | 10 | 80 | 60 | 10 | 150 | M
P41393 | Napier Road, (Former Police Station) (OTS) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2024/25 | April | 4 | 4 | 0 | 0 | 4 | 18 | 18 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2024/25 | April | 2024/25 | March |  | 0.379 | [5 empty] | 0.379 | Y |  |  | 0.379 | 0.094749 | 50 | 30 | 0 | 30 | 0 | 10 | 80 | 30 | 10 | 120 | M
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 58 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2023/24 | January | 2026/27 | June | 1.5454 | 2.8737 | [5 empty] | 4.4191 | Y | 0.7 | 0.039 | 5.1581 | 0.088933 | 50 | 30 | 80 | 70 | 0 | 20 | 80 | 150 | 20 | 250 | H
P41364 | Westwood Park | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2023/24 | August | 42 | 25 | 13 | 4 | 42 | 204 | 121 | 67 | 16 | 25 | 0 | 11 | 7 | 7 | 0 | 0 | 13 | 0 | 8 | 0 | 0 | 5 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 40.48% | 9.524% | SR | OTS | 2023/24 | August | 2025/26 | August | 1.5 | 1 | 1.2124 |  |  |  |  | 3.7124 | Y | 0.6 | 0.0357 | 4.3481 | 0.10353 | 50 | 30 | 80 | 70 | 0 | 20 | 80 | 150 | 20 | 250 | H
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | KHA | KHA | 2026/27 | January | 30 | 19 | 9 | 2 | 30 | 129 | 85 | 36 | 8 | 19 | 0 | 14 | 5 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 36.67% | 6.667% | SR | D&B | 2026/27 | January | 2028/29 | April | 0.85609 |  |  | 0.2 | 1.738 | 1 |  | 3.7941 |  |  |  | 3.7941 | 0.12647 | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | M
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | FC | FC | 2027/28 | May | 3 | 0 | 0 | 3 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2027/28 | June | 2027/28 | December |  |  |  |  | 0.28425 |  |  | 0.28425 | Y |  |  | 0.28425 | 0.094749 | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170 | M
P41400 | Daly Gardens / Woodhead Farm Road (HVF002) | High Valleyfield | West Fife Villages | Dunfermline & West Fife | FC | FC | 2025/26 | May | 20 | 14 | 5 | 1 | 20 | 91 | 66 | 21 | 4 | 14 | 0 | 7 | 6 | 1 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 5% | SR | D&B | 2025/26 | May | 2026/27 | September |  |  | 0.75 | 1.145 |  |  |  | 1.895 | Y |  |  | 1.895 | 0.094749 | 40 | 20 | 0 | 10 | 0 | 20 | 60 | 10 | 20 | 90 | M
T36239 | Echobank | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | KHA | KI | 2026/27 | September | 12 | 12 | 0 | 0 | 12 | 50 | 50 | 0 | 0 | 12 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | September | 2027/28 | March |  |  |  | 0.832 |  |  |  | 0.832 |  |  |  | 0.832 | 0.069333 | 40 | 35 | 0 | 10 | 0 | 10 | 75 | 10 | 10 | 95 | M
P47095 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2023/24 | October | 15 | 15 | 0 | 0 | 15 | 60 | 60 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2023/24 | October | 2025/26 | July | 0.25 | 0.785 | [5 empty] | 1.035 | Y |  |  | 1.035 | 0.069 | 40 | 35 | 0 | 30 | 20 | 20 | 75 | 30 | 40 | 145 | M
P41447 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2023/24 | October | 37 | 24 | 10 | 3 | 37 | 230 | 132 | 85 | 13 | 24 | 0 | 11 | 10 | 3 | 0 | 0 | 10 | 4 | 2 | 1 | 0 | 3 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 35.14% | 8.108% | SR | D&B | 2023/24 | October | 2025/26 | July | 1.05 | 2.326 | [5 empty] | 3.376 | Y |  |  | 3.376 | 0.091243 | 40 | 35 | 0 | 30 | 20 | 20 | 75 | 30 | 40 | 145 | M
P41448 | Fraser Avenue Phase 4 | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2026/27 | March | 41 | 23 | 16 | 2 | 41 | 171 | 92 | 71 | 8 | 23 | 0 | 19 | 4 | 0 | 0 | 0 | 16 | 0 | 12 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 43.9% | 4.878% | SR | D&B | 2026/27 | March | 2028/29 | October |  |  |  |  | 3.016 | 1 |  | 4.016 | Y |  |  | 4.016 | 0.097951 | 40 | 35 | 0 | 30 | 20 | 10 | 75 | 30 | 30 | 135 | M
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2025/26 | March | 45 | 29 | 14 | 2 | 45 | 189 | 116 | 65 | 8 | 29 | 0 | 18 | 11 | 0 | 0 | 0 | 14 | 0 | 8 | 3 | 3 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 35.56% | 4.444% | SR | D&B | 2025/26 | March | 2027/28 | March |  |  | 0.1 | 2.5 | 1.408 |  |  | 4.008 |  |  |  | 4.008 | 0.089067 | 40 | 35 | 10 | 10 | 0 | 10 | 75 | 20 | 10 | 105 | M
P45418 | Cochrane Street (Kelty SW SDA) | Kelty | Cowdenbeath | Dunfermline & West Fife | FC | FC | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 21 | 4 | 0 | 0 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | [5 empty] | 0.2 | 1.695 | 1.895 | Y |  |  | 1.895 | 0.094749 | 40 | 25 | 10 | 10 | 20 | 20 | 65 | 20 | 40 | 125 | M | 20 units to be delivered | 20
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | KHA | KHA | 2025/26 | August | 6 | 3 | 3 | 0 | 6 | 24 | 12 | 12 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | SR | D&B | 2025/26 | August | 2025/26 | February |  |  | 0.588 |  |  |  |  | 0.588 |  |  |  | 0.588 | 0.098 | 40 | 25 | 50 | 30 | 0 | 10 | 65 | 80 | 10 | 155 | M
P41322 | Langside Crescent Phase 2A | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | FC | FC | 2021/22 | January | 43 | 32 | 11 | 0 | 43 | 200 | 162 | 38 | 0 | 32 | 0 | 6 | 22 | 4 | 0 | 0 | 11 | 6 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.58% | 0% | SR | D&B | 2023/24 | March | 2024/25 | December | 3.2697 | [6 empty] | 3.2697 | Y | 0.5 |  | 3.7697 | 0.087667 | 50 | 50 | 80 | 70 | 0 | 20 | 100 | 150 | 20 | 270 | H
P45311 | Langside Crescent Phase 2B | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | FC | FC | 2023/24 | November | 20 | 11 | 8 | 1 | 20 | 111 | 50 | 56 | 5 | 11 | 0 | 5 | 6 | 0 | 0 | 0 | 8 | 0 | 2 | 0 | 2 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 45% | 5% | SR | D&B | 2023/24 | November | 2025/26 | April | 1.6449 | [6 empty] | 1.6449 | Y | 0.25 |  | 1.8949 | 0.094747 | 50 | 50 | 80 | 70 | 0 | 20 | 100 | 150 | 20 | 270 | H
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 78 | 0 | 0 | 0 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 11 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | [5 empty] | 2.351 | 2.351 | 4.702 |  |  |  | 4.702 | 0.097958 | 50 | 50 | 0 | 10 | 0 | 10 | 100 | 10 | 10 | 120 | M | 48 units to be delivered | 48
P46986 | Myreside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | FC | FC | 2026/27 | June | 49 | 34 | 12 | 3 | 49 | 209 | 154 | 42 | 13 | 34 | 0 | 20 | 10 | 4 | 0 | 0 | 12 | 0 | 8 | 2 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2026/27 | June | 2028/29 | June |  |  |  | 1 | 2 | 1.6427 |  | 4.6427 |  |  |  | 4.6427 | 0.094749 | 50 | 50 | 0 | 30 | 0 | 20 | 100 | 30 | 20 | 150 | M
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | FC | FC | 2026/27 | November | 40 | 27 | 9 | 4 | 40 | 177 | 123 | 37 | 17 | 27 | 0 | 12 | 9 | 6 | 0 | 0 | 9 | 0 | 6 | 1 | 0 | 2 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 32.5% | 10% | SR | D&B | 2026/27 | November | 2028/29 | October |  |  |  | 1 | 1 | 1.79 |  | 3.79 | Y |  |  | 3.79 | 0.094749 | 40 | 20 | 10 | 10 | 20 | 20 | 60 | 20 | 40 | 120 | M
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | FC | FC | 2028/29 | October | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 49 | 17 | 0 | 0 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | October | 2030/31 | October |  |  |  |  | 1 | 1 | 1.79 | 3.79 | Y |  |  | 3.79 | 0.094749 | 40 | 20 | 10 | 10 | 20 | 20 | 60 | 20 | 40 | 120 | M | 40 units to be delivered | 40
P46176 | South of Hill View | Kinglassie | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2024/25 | June | 45 | 32 | 13 | 0 | 45 | 195 | 143 | 52 | 0 | 32 | 0 | 15 | 15 | 2 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.89% | 0% | SR | D&B | 2024/25 | June | 2026/27 | October |  | 2 | 2 | 0.408 |  |  |  | 4.408 | Y |  |  | 4.408 | 0.097956 | 50 | 30 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200 | H
P45417 | Esplanade (EC Housing) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2028/29 | February | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 21 | 0 | 0 | 0 | 0 | 0 | 3 | 14 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | February | 2030/31 | January | [5 empty] | 1.1 | 2.8795 | 3.9795 | Y |  |  | 3.9795 | 0.094749 | 50 | 40 | 0 | 30 | 0 | 30 | 90 | 30 | 30 | 150 | M | 42 units to be delivered | 42
P44715 | Kingdom Park Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2027/28 | April | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 91 | 18 | 0 | 0 | 28 | 26 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2027/28 | April | 2029/30 | January |  |  |  |  | 2 | 2 | 4.2432 | 8.2432 | Y |  |  | 8.2432 | 0.094749 | 50 | 40 | 40 | 30 | 20 | 20 | 90 | 70 | 40 | 200 | H | 87 units to be delivered | 87
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC | FC | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 52 | 10 | 0 | 0 | 16 | 16 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2029/30 | March | [5 empty] | 1.2 | 3.5375 | 4.7374 | Y |  |  | 4.7374 | 0.094749 | 50 | 40 | 10 | 10 | 20 | 20 | 90 | 20 | 40 | 150 | M | 50 units to be delivered | 50
P44714 | Postings | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2027/28 | April | 25 | 17 | 6 | 2 | 25 | 109 | 75 | 26 | 8 | 17 | 0 | 7 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2027/28 | April | 2028/29 | May |  |  |  |  | 1.9187 |  |  | 1.9187 | Y | 0.45 |  | 2.3687 | 0.094749 | 50 | 40 | 0 | 30 | 20 | 20 | 90 | 30 | 40 | 160 | M
P46106 | Templehall Regeneration Phase 2 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2027/28 | July | 12 | 8 | 0 | 4 | 12 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2027/28 | July | 2028/29 | July |  |  |  |  | 0.83699 |  |  | 0.83699 | Y | 0.3 |  | 1.137 | 0.094749 | 50 | 40 | 0 | 30 | 20 | 20 | 90 | 30 | 40 | 160 | M
P46177 | Templehall Regeneration Phase 3 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KI | 2027/28 | July | 12 | 12 | 0 | 0 | 12 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | July | 2028/29 | July |  |  |  |  | 0.831 |  |  | 0.831 | Y |  |  | 0.831 | 0.06925 | 50 | 40 | 0 | 30 | 20 | 10 | 90 | 30 | 30 | 150 | M
P41320 | Union Street MS | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC | FC | 2028/29 | May | 3 | 0 | 0 | 3 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | [5 empty] | 0.28425 |  | 0.28425 | Y |  |  | 0.28425 | 0.094749 | 50 | 40 | 50 | 10 | 20 | 30 | 90 | 60 | 50 | 200 | H
P43402 | Viewforth High School | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2022/23 | March | 15 | 10 | 5 | 0 | 15 | 64 | 42 | 22 | 0 | 10 | 0 | 8 | 2 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.33% | 0% | SR | D&B | 2022/23 | March | 2024/25 | August | 1.4974 | [6 empty] | 1.4974 |  |  |  | 1.4974 | 0.099829 | 50 | 40 | 90 | 70 | 0 | 10 | 90 | 160 | 10 | 260 | H
T33940 | Ingrie Farm | Leslie | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2023/24 | July | 44 | 32 | 12 | 0 | 44 | 199 | 151 | 48 | 0 | 32 | 0 | 14 | 13 | 5 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.27% | 0% | SR | D&B | 2023/24 | August | 2024/25 | February | 3.174 | 2.363 | [5 empty] | 5.537 |  |  |  | 5.537 | 0.12584 | 50 | 30 | 80 | 70 | 0 | 10 | 80 | 150 | 10 | 240 | H
P43196 | Pitlethie Road | Leuchars | St Andrews | St Andrews & East Fife | KHA | KHA | 2023/24 | January | 49 | 36 | 10 | 3 | 49 | 224 | 163 | 48 | 13 | 36 | 0 | 19 | 15 | 2 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 26.53% | 6.122% | SR | D&B | 2023/24 | January | 2025/26 | March | 1.684 | 1.8 | 1.316 |  |  |  |  | 4.8 |  |  |  | 4.8 | 0.097959 | 30 | 5 | 50 | 30 | 0 | 20 | 35 | 80 | 20 | 135 | M
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | KHA | KHA | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 64 | 0 | 0 | 0 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 0.68828 |  |  |  |  | 3.916 |  | 4.6043 |  |  |  | 4.6043 | 0.10009 | 30 | 5 | 50 | 30 | 0 | 10 | 35 | 80 | 10 | 125 | M | 46 units to be delivered | 46
P45421 | Park Drive (EHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | FC | FC | 2024/25 | April | 29 | 19 | 6 | 4 | 29 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2024/25 | September | 2025/26 | December | 0.387 | 0.5 | 1.4586 |  |  |  |  | 2.3456 | Y | 0.4 | 0.0021 | 2.7477 | 0.094749 | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220 | H
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | KHA | OVHA | 2023/24 | January | 47 | 37 | 10 | 0 | 47 | 145 | 109 | 36 | 0 | 37 | 19 | 17 | 0 | 1 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.28% | 0% | SR | D&B | 2023/24 | January | 2025/26 | November | 0.80935 | 1.897 | 1.897 |  |  |  |  | 4.6033 | Y |  |  | 4.6033 | 0.097944 | 40 | 25 | 50 | 30 | 20 | 10 | 65 | 80 | 30 | 175 | H
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 44 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2023/24 | February | 2025/26 | March | 1.123 | 2.2289 | [5 empty] | 3.3519 | Y |  |  | 3.3519 | 0.07618 | 40 | 25 | 80 | 70 | 0 | 30 | 65 | 150 | 30 | 245 | H
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 51 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2024/25 | September | 4.2308 | [6 empty] | 4.2308 | Y |  | 0.00815 | 4.2389 | 0.083116 | 40 | 25 | 80 | 70 | 0 | 20 | 65 | 150 | 20 | 235 | H
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | KHA | KHA | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 26 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2029/30 | February | [5 empty] | 1.665 |  | 1.665 |  |  |  | 1.665 | 0.097941 | 30 | 45 | 10 | 30 | 0 | 20 | 75 | 40 | 20 | 135 | M | 17 units to be delivered | 17
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | KHA | KHA | 2028/29 | January | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 32 | 4 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | June | [5 empty] | 0.25 | 1.709 | 1.959 | Y |  |  | 1.959 | 0.09795 | 40 | 25 | 0 | 10 | 0 | 10 | 65 | 10 | 10 | 85 | M | 20 units to be delivered | 20
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 97 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2024/25 | December | 6.9498 | [6 empty] | 6.9498 | Y | 1.65 |  | 8.5998 | 0.088658 | 40 | 25 | 80 | 70 | 20 | 20 | 65 | 105 | 40 | 210 | H
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 25 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June |  |  |  |  | 1.7 | 0.66873 |  | 2.3687 | Y |  |  | 2.3687 | 0.094749 | 50 | 30 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110 | M
P44709 | High Street (OTS) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2022/23 | October | 8 | 6 | 2 | 0 | 8 | 48 | 32 | 16 | 0 | 6 | 0 | 0 | 4 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | SR | D&B | 2023/24 | April | 2024/25 | April |  | 0.73728 | [5 empty] | 0.73728 | Y |  |  | 0.73728 | 0.09216 | 50 | 50 | 80 | 70 | 20 | 20 | 100 | 150 | 40 | 290 | H
P45416 | Methilhaven Road (Former Care Home) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | FC | FC | 2026/27 | September | 40 | 28 | 9 | 3 | 40 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2026/27 | September | 2027/28 | January |  |  |  | 1.5 | 1.4162 |  |  | 2.9162 | Y | 0.4 |  | 3.3162 | 0.082905 | 50 | 50 | 50 | 30 | 20 | 20 | 100 | 80 | 40 | 220 | H
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | GHA | 2025/26 | November | 6 | 4 | 1 | 1 | 6 | 28 | 20 | 4 | 4 | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 16.67% | SR | D&B | 2025/26 | November | 2026/27 | July |  |  | 0.588 |  |  |  |  | 0.588 |  |  |  | 0.588 | 0.098 | 50 | 30 | 10 | 30 | 0 | 20 | 80 | 40 | 20 | 140 | M
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | FC | FC | 2023/24 | August | 34 | 28 | 5 | 1 | 34 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2023/24 | September | 2025/26 | August | 1.5 | 1.434 | [5 empty] | 2.934 | Y | 0.5 | 0.013 | 3.447 | 0.10138 | 20 | 15 | 30 | 70 | 0 | 10 | 35 | 100 | 10 | 145 | M
P46107 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | FC PSD | FC | 2026/27 | October | 8 | 6 | 1 | 1 | 8 | 38 | 30 | 4 | 4 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 25% | 12.5% | SR | D&B | 2026/27 | October | 2027/28 | October |  |  |  | 0.75799 |  |  |  | 0.75799 | Y |  |  | 0.75799 | 0.094749 | 30 | 45 | 0 | 10 | 0 | 20 | 75 | 10 | 20 | 105 | M
P43399 | Station Court | Pittenweem | Largo & East Neuk | St Andrews & East Fife | KHA | KHA | 2023/24 | September | 29 | 21 | 7 | 1 | 29 | 132 | 96 | 32 | 4 | 21 | 0 | 11 | 8 | 2 | 0 | 0 | 7 | 0 | 6 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.59% | 3.448% | SR | D&B | 2023/24 | September | 2024/25 | September | 1.0517 | 1.789 | [5 empty] | 2.8407 |  |  |  | 2.8407 | 0.097954 | 30 | 45 | 80 | 70 | 0 | 20 | 75 | 150 | 20 | 245 | H
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | FHG | FHG | 2025/26 | April | 38 | 27 | 9 | 2 | 38 | 173 | 125 | 40 | 8 | 27 | 0 | 13 | 12 | 2 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.95% | 5.263% | SR | D&B | 2025/26 | April | 2026/27 | December |  |  | 1 | 2.724 |  |  |  | 3.724 |  |  |  | 3.724 | 0.098 | 40 | 35 | 50 | 30 | 0 | 10 | 75 | 80 | 10 | 165 | M
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2024/25 | August | 30 | 14 | 13 | 3 | 30 | 124 | 84 | 32 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 13 | 0 | 5 | 2 | 0 | 6 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 53.33% | 10% | SR | D&B | 2024/25 | August | 2025/26 | September | 0.41 | 0.5 | 1.6325 |  |  |  |  | 2.5425 | Y | 0.3 |  | 2.8425 | 0.094749 | 40 | 35 | 50 | 30 | 0 | 30 | 75 | 80 | 30 | 185 | H
P47097 | Hilton Gardens | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | KHA | KHA | 2028/29 | October | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 32 | 4 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | October | 2029/30 | March | [5 empty] | 0.6 | 1.359 | 1.959 |  |  |  | 1.959 | 0.09795 | 40 | 35 | 10 | 30 | 0 | 10 | 75 | 40 | 10 | 125 | M | 20 units to be delivered | 20
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | FHG | FHG | 2026/27 | June | 25 | 18 | 6 | 1 | 25 | 113 | 83 | 26 | 4 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2026/27 | August | 2027/28 | August |  |  |  | 1.35 | 1.1 |  |  | 2.45 |  |  |  | 2.45 | 0.098 | 40 | 35 | 50 | 10 | 0 | 10 | 75 | 60 | 10 | 145 | M
P43425 | Whinnyburn Phase 2 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | FHG | FHG | 2027/28 | July | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 40 | 8 | 0 | 0 | 14 | 8 | 6 | 0 | 0 | 0 | 0 | 6 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2027/28 | September | 2029/30 | May |  |  |  |  | 1.5 | 1.5 | 0.9 | 3.9 |  |  |  | 3.9 | 0.0975 | 40 | 35 | 50 | 10 | 0 | 10 | 75 | 60 | 10 | 145 | M | 40 units to be delivered | 40
P41382 | West Road (includes EC Housing) | Saline | West Fife Villages | Dunfermline & West Fife | FC | FC | 2022/23 | March | 39 | 15 | 20 | 4 | 39 | 159 | 75 | 68 | 16 | 15 | 0 | 5 | 5 | 5 | 0 | 0 | 20 | 6 | 14 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 61.54% | 10.26% | SR | D&B | 2022/23 | March | 2024/25 | January | 3.4772 | [6 empty] | 3.4772 | Y |  |  | 3.4772 | 0.089158 | 40 | 20 | 80 | 70 | 0 | 30 | 60 | 150 | 30 | 240 | H
P43185 | Crawley Court | Springfield | Cupar & HOF | Cupar & North West Fife | FC PSD | FC | 2021/22 | February | 30 | 22 | 6 | 2 | 30 | 140 | 108 | 24 | 8 | 22 | 0 | 6 | 12 | 4 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 26.67% | 6.667% | SR | D&B | 2022/23 | July | 2024/25 | April | 2.6344 | [6 empty] | 2.6344 | Y |  |  | 2.6344 | 0.087813 | 20 | 10 | 80 | 70 | 0 | 20 | 30 | 150 | 20 | 200 | H
P44067 | Manse Road | Springfield | Cupar & HOF | Cupar & North West Fife | FC PSD | FC | 2023/24 | August | 30 | 21 | 7 | 2 | 30 | 147 | 108 | 31 | 8 | 21 | 0 | 2 | 14 | 5 | 0 | 0 | 7 | 0 | 6 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 6.667% | SR | D&B | 2023/24 | September | 2025/26 | August | 1.5 | 0.8 | 0.47405 |  |  |  |  | 2.774 | Y | 0.5 |  | 3.274 | 0.10913 | 20 | 10 | 80 | 70 | 0 | 20 | 30 | 150 | 20 | 200 | H
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | FC | FC | 2027/28 | May | 2 | 0 | 0 | 2 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2027/28 | June | 2027/28 | December |  |  |  |  | 0.1895 |  |  | 0.1895 | Y |  |  | 0.1895 | 0.094749 | 30 | 5 | 50 | 10 | 20 | 30 | 35 | 60 | 50 | 145 | M
P43392 | Kilrymont Road | St Andrews | St Andrews | St Andrews & East Fife | FC | FC | 2024/25 | April | 32 | 22 | 8 | 2 | 32 | 143 | 101 | 38 | 4 | 22 | 0 | 11 | 8 | 3 | 0 | 0 | 8 | 0 | 5 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 31.25% | 6.25% | SR | D&B | 2024/25 | April | 2025/26 | September |  | 0.8 | 1.532 |  |  |  |  | 2.332 | Y | 0.7 |  | 3.032 | 0.094749 | 30 | 5 | 30 | 30 | 0 | 20 | 35 | 60 | 20 | 115 | M
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | FC | FC | 2029/30 | April | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 42 | 40 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | April | 2030/31 | March | [5 empty] | 1.2 | 2.59 | 3.79 | Y |  |  | 3.79 | 0.094749 | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | M | 40 units to be delivered | 40
P41481 | North Haugh Phase 2 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | FC | FC | 2029/30 | April | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 42 | 42 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | April | 2030/31 | March | [5 empty] | 1.2 | 2.59 | 3.79 | Y |  |  | 3.79 | 0.094749 | 30 | 5 | 10 | 10 | 20 | 20 | 35 | 20 | 40 | 95 | M | 40 units to be delivered | 40
P41506 | Younger Gardens (Craigtoun) Ph1 (STA001 Sth) | St Andrews | St Andrews | St Andrews & East Fife | KHA | KHA | 2022/23 | February | 34 | 22 | 10 | 2 | 34 | 165 | 109 | 46 | 10 | 22 | 0 | 7 | 9 | 6 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 35.29% | 5.882% | SR | D&B | 2022/23 | February | 2025/26 | August | 1.6 | 1.656 | [5 empty] | 3.256 |  |  | 0.68855 | 3.9446 | 0.11602 | 30 | 5 | 40 | 70 | 0 | 20 | 35 | 110 | 20 | 165 | M
P41507 | Younger Gardens Ph2 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | KHA | KI | 2023/24 | January | 9 | 9 | 0 | 0 | 9 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2023/24 | February | 2024/25 | September |  | 0.623 | [5 empty] | 0.623 |  |  |  | 0.623 | 0.069222 | 30 | 5 | 40 | 70 | 0 | 10 | 35 | 110 | 10 | 155 | M
P45409 | Younger Gardens Ph2 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | KHA | KHA | 2023/24 | January | 12 | 8 | 4 | 0 | 12 | 57 | 35 | 22 | 0 | 8 | 0 | 5 | 3 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.33% | 0% | SR | D&B | 2023/24 | February | 2024/25 | September |  | 1.176 | [5 empty] | 1.176 |  |  |  | 1.176 | 0.098 | 30 | 5 | 40 | 70 | 0 | 10 | 35 | 110 | 10 | 155 | M
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | KHA | KI | 2026/27 | April | 29 | 29 | 0 | 0 | 29 | 116 | 116 | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | April | 2027/28 | March |  |  |  | 2.01 |  |  |  | 2.01 |  |  |  | 2.01 | 0.06931 | 30 | 5 | 40 | 70 | 0 | 10 | 35 | 110 | 10 | 155 | M
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | KHA | KHA | 2026/27 | April | 19 | 11 | 8 | 0 | 19 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2026/27 | April | 2027/28 | March |  |  |  | 1.861 |  |  |  | 1.861 |  |  |  | 1.861 | 0.097947 | 30 | 5 | 40 | 70 | 0 | 10 | 35 | 110 | 10 | 155 | M
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | FC PSD | FC | 2024/25 | April | 30 | 20 | 9 | 1 | 30 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | April | 2025/26 | June |  | 0.8 | 1.9211 |  |  |  |  | 2.7211 | Y |  | 0.12135 | 2.8425 | 0.094749 | 30 | 5 | 30 | 70 | 0 | 20 | 35 | 100 | 20 | 155 | M
P43391 | Cash Feus (EHDP) | Strathmiglo | Cupar & HOF | Cupar & North West Fife | FC | FC | 2025/26 | April | 14 | 10 | 2 | 2 | 14 | 43 | 32 | 6 | 5 | 10 | 0 | 8 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2025/26 | April | 2025/26 | March | 0.34619 |  | 0.9803 |  |  |  |  | 1.3265 | Y |  |  | 1.3265 | 0.094749 | 20 | 10 | 50 | 10 | 20 | 30 | 30 | 60 | 50 | 140 | M
P44739 | Bell Street | Tayport | Tay Coast | Greater Dundee | KHA | KHA | 2027/28 | January | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 80 | 8 | 0 | 0 | 21 | 8 | 0 | 0 | 0 | 0 | 0 | 12 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2027/28 | January | 2029/30 | August |  |  |  |  | 1.2 | 3.6 |  | 4.8 |  |  |  | 4.8 | 0.097959 | 30 | 15 | 0 | 30 | 0 | 10 | 45 | 30 | 10 | 85 | M | 49 units to be delivered | 49
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December | [5 empty] | 0.1895 |  | 0.1895 | Y |  |  | 0.1895 | 0.094749 | 30 | 15 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155 | M
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2027/28 | April | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2027/28 | April | 2029/30 | March |  |  |  |  | 1 | 1.8 | 1.9374 | 4.7374 | Y |  |  | 4.7374 | 0.094749 | 50 | 30 | 10 | 30 | 20 | 20 | 80 | 40 | 40 | 160 | M | 50 units to be delivered | 50
P46179 | Strathore Road - Thornton SLA Phase 2 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2028/29 | February | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 46 | 14 | 0 | 0 | 15 | 14 | 6 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | February | 2030/31 | March | [5 empty] | 0.5 | 3.95 | 4.45 | Y |  |  | 4.45 | 0.089 | 50 | 30 | 10 | 30 | 20 | 10 | 80 | 40 | 30 | 150 | M | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | FC | FC | 2027/28 | April | 2 | 0 | 0 | 2 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2027/28 | April | 2027/28 | December |  |  |  |  | 0.1895 |  |  | 0.1895 | Y |  |  | 0.1895 | 0.094749 | 40 | 35 | 50 | 10 | 20 | 30 | 75 | 60 | 50 | 185 | H
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | KHA | GHA | 2024/25 | May | 8 | 7 | 1 | 0 | 8 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2024/25 | May | 2024/25 | March |  | 0.784 | [5 empty] | 0.784 | Y |  |  | 0.784 | 0.098 | 50 | 50 | 30 | 70 | 0 | 10 | 100 | 100 | 10 | 210 | H
957
[9 empty] | 3051 | 2095 | 759 | 197 | 3051 | 13256 | 12064 | 4340 | 1081 | 2095 | 59 | 1299 | 1082 | 256 | 2 | 0 | 759 | 128 | 704 | 75 | 49 | 89 | 2 | 197 | [6 empty] | 31.33% | 6.457% | [6 empty] | 65.8745 | 49.835 | 49.656 | 48.3193 | 45.9557 | 41.2626 | 46.1802 | 347.0833 |  | 14.65 | 1.2976 | 363.0308

## Codes
This sheet has all the options for the dropdown lists on the main sheet. Blank rows have been left to allow extra options to be added in the future - please do not delete them.
SLP Status
17/18
18/19
19/20 | Priority
20/21 | L
21/22 | M
22/23 | H
23/24
Developer
FC
FC PSD
KHA
KI
FHG
OVHA
Landlord
FC
FC PSD
KHA
KI
FHG (A)
OVHA
GHA
FHG
LHS Area |  | HMA Area
Glenrothes |  | Dunfermline & West Fife
Kirkcaldy |  | Kirkcaldy, Glenrothes & Central
Levenmouth |  | Cupar & North West Fife
Dunfermline & Coast |  | St Andrews & East Fife
Cowdenbeath |  | Greater Dundee
West Fife Villages
Cupar & HOF
Largo & East Neuk
St Andrews
Tay Coast
SG Tender Approval Year
2017/18
2018/19
2019/20
2020/21
2021/22
2022/23
2023/24
2024/25
2025/26
2026/27
2027/28
2028/29
2029/30
2030/31
Tenure
SR
MMR 30
MMR 5
PSR
Other
Contract Type
D&B
OTS
FC BS
Staged
SCAPE
Change Control
Add - to be approved
Removed - to be approved
Other Change - lead delivery partner
Other Change - see comments
Stage
0 - Feasibility
1 - Dev Mix & brief
2 - design, plg & acq
3 - Contract Neg/tender approval
4 - on site
5 - completed
Block
A
B
Shadow
Programmed/Potential
Programmed
Potential
Phase 4
Shadow
Below List